## Sheet1
Group Number: |  | 17
Group Members: |  | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík
Mentor: |  | Edirlei de Lima-Soares
Date | Type of Meeting (Standup / Retro) | Attendees | Link to Recording | Summary of Meeting
2025-05-20 | Presentations | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík, Edirlei de Lima-Soares | None | We presented our individual proposals and began working out how to combine them.
2025-05-23 | Retrospective | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík, Edirlei de Lima-Soares | https://trello.com/invite/b/682f0d34885c7c287fcaae7c/ATTI0987824246b1d8bfa89405ef1285b2b609DBA9E0/235retrospective | Our first retrospective, where we went through the steps to hold one with our mentor.
2025-05-26 | Standup | Maks Burchard, Ceren Kurt, Zofia Piliwska, Filip Šarík | Stand-up meeting Week 4 Monday-20250526_103241-Opname van vergadering.mp4 | We talked about the Project Proposal and divided tasks regarding that and data anlysis.
2025-05-27 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | We talked about the work we did on Monday and divided up the tasks for today, and set up action points to ask for clarifications.
2025-05-27 | Retrospective | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík, Edirlei de Lima-Soares | Link to Retrospective | Our second retrospective, where we mainly discussed the points that were negative, and created action points to solve them.
2025-05-27 | Meeting | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | After the retrospective, one of our action points was to have a meeting to discuss the deadlines. This was that meeting, and we discussed how we should plan in our deadlines.
2025-05-28 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | Link to recording | We spoke mainly about administrative tasks such as the deadlines, GitHub, and the project managers for the next few weeks.
2025-06-02 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | Link to recording | We began talking about and divided the tasks with regards to the modeling of the model.
2025-06-03 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | We divided most of the important tasks yesterday and this was more about the continuation of the tasks.
2025-06-04 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | Link to Recording | First we discussed the improvements we need to implement to trello board, then we decided to share one group meeting log to OneDrive. We also clarified the way we want to tackle the model training, divided the work and start experimenting with Streamlit
2025-06-05 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | Link to Recording | Discussed how is the modeling going. Clarified some things about the modeling. Decided to upload these notebooks on GitHub for further review
2025-06-06 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | Reviewed how the modeling work is going. Discussed the project shift about choosing only specific company.
2025-06-06 | Retrospective | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík, Edirlei de Lima-Soares | https://trello.com/invite/b/6842aedb83bf68a342aa240d/ATTIa9baf3b303cb1485e20cf9f666fa0bbd39746773/retrospective662025 | Discussed action points, discussed how we want to move next. Went through some important requirements. Refreshed all the tasks that need to be done.
2025-06-10 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | Discussed model progress, assigned responsibilities for completing models and the Streamlit dashboard, planned stakeholder communication post-development, reviewed Trello tasks, and set clear deadlines and action points.
2025-06-11 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | Microsoft Teams meeting-20250611_103008-Meeting Recording.mp4 | The team discussed model performance, dashboard development, and integration into a Poetry-managed environment, assigning specific responsibilities for each task. Filip and Ceren will upload code and models, Zofia will finalize the dashboard, and Maks will organize the project code for the MLOps template, all by the 12th of June.
2025-06-12 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | https://edubuas-my.sharepoint.com/:v:/g/personal/243537_buas_nl/EeSUi1z9KHxBrEMqu53EuKQBWD1DV2CJifqEyan1IuvurQ?e=ayYYWb&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | The team made progress on the final project with Filip finalizing the classification model and Ceren preparing to upload her parts after resolving technical issues. Zofia improved the dashboard and began working on the final presentation and README. The MLOps part—template completion and Poetry environment integration—still needs to be completed by Maks.
2025-06-13 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | None | Today, the team reviewed the progress on the final project, identifying that the results table and problem statement still need to be completed by Ceren, while Maks continues work on the Poetry environment, MLOps tasks, and Filip on stakeholder coordination. Zofia is fixing the dashboard and starting on the README, and the team agreed to begin working on the final presentation next week.
2025-06-13 | Meeting with stakeholder | Zofia Pilitowska, Filip Šarík | None | In the meeting with our stakeholder, our project idea was approved, and we received positive feedback on the dashboard’s user interface. We were encouraged to further improve the functionality by combining the outputs of the regression and classification models to enhance the reliability of our recommendations. Additionally, it was suggested that we clearly explain our feature selection process in the project proposal to provide better context for our modeling choices.
2025-06-16 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | https://edubuas-my.sharepoint.com/:v:/g/personal/243910_buas_nl/EYFdO6xp-OFLkZfNTyjFZksBA4eqe-I3imrRv1M2BYlQyQ?e=stgB0L&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | We planned to finish the dashboard and fix Poetry today, then focus on finalizing and practicing the presentation together tomorrow
2025-06-17 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska | None | We planned the presentation and divided everyone's tasks for the presentation.
2025-06-17 | Retrospective | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík, Edirlei de Lima-Soares | https://trello.com/invite/b/685157190b9cc1675d56d35c/ATTI90b07c9e717a3b0805ce86a975422f8b6849CAA9/1762025retrospective | We did many things well throughout the project, but we also noticed some issues with timing and communication, so we talked about how we can improve them together.
2025-06-18 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | https://edubuas-my.sharepoint.com/:v:/g/personal/243910_buas_nl/Ec0M4Vp6WvxJnOwccGW2pEQBJyKh4NIUQe-WBk1Y3bCHlw?e=LWRf1I&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | We discussed final tasks like completing the presentation, adding the demo video, uploading poetry setup screenshots, and preparing the Docker file and README instructions
2025-06-19 | Standup | Maks Burchard, Ceren Kurt, Zofia Pilitowska, Filip Šarík | https://edubuas-my.sharepoint.com/:v:/g/personal/243910_buas_nl/EeC_TEbXQqxGjHJrZy3SdUwB0WY4-olkXDsWQyPEGs_mWw?e=dNAeSa&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | In our final stand-up, we went over wrapping up templates, finalizing the presentation, checking poetry setup and README instructions, and making sure everyone stays within the time limit for tomorrow’s demo.