## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
0
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 1 Evidence | This section is for all evidence linked in Week 1, and you can find it divided by days below | Evidencing |  | 0 | 0 | 0 |  | https://github.com/BredaUniversityADSAI/2024-25c-fai1-adsai-CerenKurt243910/tree/main/Week%201
2025-02-10 | Done | PlantNet App Analysis | I reviewed PlantNet to understand its identification features and user experience. | Research | ILO 2.3 | 1 | 1 | 0 | PlantNet | The app provides plant recognition but lacks disease detection and care recommendations
| Done | PictureThis App Review | I analyzed PictureThis to compare its plant identification accuracy and additional features. | Research | ILO 2.4 | 1 | 1 | 0 | PictureThis | While the app includes plant care tips, its recommendations are too generic and not customized
| Done | AlgorithmWatch Review | I reviewed AlgorithmWatch’s analysis on plant identification apps to understand their limitations. | Research | ILO 2.3 | 1 | 1 | 0 | AlgorithmWatch | The report highlights that these apps often misidentify plants and lack real-time monitoring
| Done | DAPS Diagram & Business Value Analysis | I read the paper ‘DAPS diagrams for defining Data Science projects’ to better understand how to structure business value within my project. | Research | ILO 2.3 | 1 | 1 | 0 | DAPS Diagram Paper | The paper helped me understand how to connect my project’s impact to business goals. This made defining the business value in my DAPS diagram clearer.
| Done | DAPS Diagram & Business Value | I created a DAPS diagram to define how AI-powered image classification helps plant care. | Study | ILO 2.3 | 2 | 2 | 0 | DAPS Diagram Evidence | The DAPS diagram was a bit challenging, but it helped structure the problem clearly.
2025-11-02 | Done | Business Understanding Template | I completed the Business Understanding Template, defining the problem, market needs, and stakeholders. | Study | ILO 3.2 | 3 | 3.5 | 0.5 | Template Evidence | The template was clear but required research to align my idea with business value.
| Done | HCAI Video Analysis | I watched a video on Human-Centered AI to understand how ML can enhance user experience while staying user-focused. | Study | ILO 2.3 | 0.5 | 0.5 | 0 | AI Products Video | The video helped me see the importance of designing AI systems that empower users rather than control them.
| Done | HCAI Article Review | I read an article on Human-Centered Machine Learning to explore how AI can be designed with a user-first approach | Study | ILO 2.3 | 1 | 1 | 0 | Article Evidence | The article gave me insights into making AI more transparent, fair, and user-friendly
2025-12-02 | Done | Extended Mind & AI | I watched a lecture on the Extended Mind Hypothesis and Network Enabled Cognition to understand how humans process information and interact with AI. | Study | ILO 2.3 | 0.5 | 0.5 | 0 | Extended Mind Video | This theory helped me see AI as an extension of human cognition, improving decision-making and problem-solving.
| Done | Extended Mind – Paper | I read an academic paper on the Extended Mind Hypothesis to explore how technology, including AI, enhances human cognition. | Research | ILO 2.3 | 1 | 1 | 0 | Extended Mind Paper | The paper provided deeper insights into how AI can function as an external memory and thinking tool for users
| Done | Design Thinking Video | I completed a LinkedIn Learning course on Design Thinking to understand structured problem-solving methods and their role in product development | Study | ILO 4.1 | 0.5 | 0.5 | 0 | Linkedln Course Evidence | This course helped me see how structured design processes improve innovation, collaboration, and efficiency in AI-driven projects
2025-02-13 | Done | Divergent vs. Convergent Thinking | I watched a video explaining the difference between divergent and convergent thinking in problem-solving. | Study | ILO 6.2 | 0.5 | 0.5 | 0 | Divergent Video | The video helped me understand when to generate multiple ideas (divergent) and when to refine them into a single best solution
| Done | High-Level Design & AI Solutions | I completed the Practical Assignment (Week 1, Wednesday) quiz on Brightspace, answering questions about problem definition, stakeholder analysis, and AI-driven solutions in high-level design. | Study | ILO 2.3 | 2 | 2.5 | 0.5 | Practical Assignment Quiz | This quiz helped me refine my problem statement and evaluate different solutions while considering AI’s role in optimizing user experience
| Done | Fairness & Bias Quiz | I learned about fairness, bias, equality, and equity. I also gave examples and reflected on how things like maps or datasets can create bias. | Study | ILO 2.3 | 3 | 2.5 | 0 | Fairness Quiz Evidence | I didn’t realize how easy it is to have bias without noticing. It really made me think.
14/2/25 | Done | Dataset Bias Analysis | I examined my plant health dataset to identify possible bias and described how it could affect model accuracy | Study | ILO 3.2 | 1 | 1 | 0 | Responsible AI Template – Task 2.2 section | I learned that even plants can reflect bias if the context isn’t diverse enough.
| Done | Image Dataset & Bias Analysis | I created an image dataset using web scraping and documented the steps. Then I analyzed bias in my dataset using examples and linked it to fairness concepts | Study | ILO 2.3 | 4 | 4 | 0 | Image dataset folder, bias analysis in Responsible AI Template, completed DL template (Task 3.1) | It was interesting to see how bias can exist even in small details like image selection. I didn’t think about that before
|  |  |  | Total Hours |  | 23 | 23.5 | 0.5
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
ALL WEEK | Done | All Week 2 Evidence | This section is for all evidence linked in Week 2, and you can find it divided by days below | Evidencing |  | 0 | 0 | 0 |  | https://github.com/BredaUniversityADSAI/2024-25c-fai1-adsai-CerenKurt243910/tree/main/Week%202
17/2/25 | Done | Individual & Group Fairness | I studied fairness in AI by exploring individual and group fairness concepts. I answered questions about bias types, fairness metrics, and fairness worldviews like WAE and WYSIWYG | Study | ILO 2.3 | 3 | 3.5 | 0.5 | Quiz Evidence | I realized that what's fair for a group might not feel fair to individuals, and different fairness metrics can lead to different ethical decisions
| Done | AI Fairness Blog | I read RStudio’s blog on AI fairness, which helped me connect concepts like group vs. individual fairness, bias sources, and fairness metrics. | Research | ILO 2.3 | 1 | 1 | 0 | Blog Evidence | It made fairness concepts feel more practical and clarified how different fairness metrics apply to real-world problems.
| Done | Fairness in Binary Classification | I explored Google’s interactive tutorial on discrimination in ML and learned how bias can sneak into binary classifiers and how to reduce it. | Research | ILO 2.3 | 1 | 1 | 0 | Tutorial screenshots | It showed me how easily models can be unfair without proper attention and how tweaking thresholds or datasets can improve fairness.
| Done | Fairness Infographic | I created a detailed infographic explaining group fairness metrics in machine learning, including a real-world use case and visual comparisons between three key metrics | Study | ILO 3.2 | 2 | 2.5 | 0.5 | Group Fairness Infographic | This task helped me better understand how different fairness metrics apply in practice and how to communicate them clearly.
| Done | Responsible AI Template Completion | Filled out the full Responsible AI Template for Task 2.3 and 2.4. This included proposing an individual fairness method, documenting the infographic process, peer feedback, improvement steps, and reflection. | Study | ILO 3.2 | 1 | 1 | 0 | Responsible Ai Template | It was useful to articulate my thought process and justify my design and method choices. Writing everything down helped me better connect theory with practical application.
2025-02-18 | Done | Guest Lecture: Group Fairness | I attended the guest lecture by Marco Favier on group fairness in AI. The session provided deeper insights into how mathematical concepts are used to measure and improve fairness in ML models. | Lecture | ILO 3.2 | 1 | 1 | 0 |  | It helped me see the real-world impact of group fairness metrics and why they matter beyond just academic definitions.
| Done | MPublic Speaking Lecture | I participated in the public speaking session by Bert Heesakkers. | Lecture | ILO 4.1 | 1 | 1 | 0 |  | I realized that public speaking is more about connection and clarity than perfection. It gave me confidence for future presentations.
| Done | Fairness Compass Resource Integration | I reviewed the AXA Fairness Compass interactive tool to better understand and compare different group fairness metrics in machine learning. | Study | ILO 2.3 | 1 | 1 | 0 | AXA Fairness Compass | The tool helped me visualize complex metrics and decide which ones were most appropriate for my dataset and use case.
2025-02-20 | Done | Group Fairness Practical Assignment | I completed the optional practical assignment by writing a Jupyter Notebook that calculates three fairness metrics using gender-based confusion matrices. | Study | ILO 2.3 | 2 | 1.5 | -1 | Fairness Metrics Analysis | This task helped me understand how bias can be revealed through simple metrics and how math supports fairness evaluation.
| Done | Introduction to Deep Learning | I studied Chapters 1 and 2 from Deep Learning with Python and completed the first two chapters of the DataCamp course Introduction to Deep Learning with Keras. | Research | ILO 4.1 | 2 | 2 | 0 | Chapters 1 & 2 | Helped me understand the difference between machine learning and deep learning more clearly. I learned how Sequential models and Dense layers work in Keras, and got familiar with essential concepts like tensors and loss functions
| Done | DataCamp Progress | Completed Chapters 1 & 2, practiced building Sequential models with Dense layers and activation functions. | Study | ILO 4,1 | 4 | 5 | 1 | DataCamp Cercifitace | Helped me understand how to structure and train basic neural networks. Keras made things feel beginner-friendly
| Done | Deep Learning Quiz Responses | I answered quiz questions on Sequential models, Dense layers, Keras functions, loss functions, and tensor attributes. | Study | ILO 1.3 | 3 | 3 | 0 | Quiz Evidence Deep Learing | The quiz reinforced my understanding of neural network layers, loss functions, and tensors
21/2/25 | Done | Package Installation for Deep Learning | Installed required packages for deep learning (NumPy, Pandas, TensorFlow, etc.) in a new conda environment. | Study | ILO 3.2 | 1 | 1 | 0 | Package list and installation | Successfully set up the environment, ensuring compatibility with the deep learning module's requirements.
| Done | Model Training and Evaluation | Ran model training for 5 epochs on the MNIST dataset and evaluated its accuracy on the test set. | Study | ILO 2.3 | 1 | 1 | 0 | Screenshot of training process | Achieved a test accuracy of 97.97%, confirming the model's effectiveness.
| Done | Normalization for Machine Learning Model | I applied normalization to the Mean Radius and Mean Fractal Dimension columns, scaling them to the 0-1 range, and compared the histograms before and after normalization. | Study | ILO 4.1 | 1 | 2 | 1 | Normalized data and histograms. | This process will help the model learn faster and reduce the impact of features with different scales.
| Done | Exact Match Ratio Calculation | Generated predictions using model.predict(), applied a 0.5 threshold, and calculated the Exact Match Ratio by comparing with y_test | Study | ILO 2.3 | 3 | 4 | 1 | Code Evidence | This metric evaluates the model's accuracy in multi-label classification tasks.
| Done | Research on Normalizer from Scikit-learn | Investigated the usage of Normalizer from Scikit-learn for scaling feature vectors in machine learning models. | Research | ILO 1.3 | 1 | 1 | 0 | Scikit-learn | This normalization technique ensures that each feature vector has unit norm, which can be beneficial for certain algorithms, like SVMs and k-NN, where distance metrics are crucial.
|  |  |  | Total Hours |  | 29 | 32.5 | 3.5
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 3 Evidence | This section is for all evidence linked in Week 3, and you can find it divided by days below | Evidencing |  | 0 | 0 | 0
2025-02-24 | Done | Training the IMDB Movie Reviews Model | I trained the model using the IMDB dataset, performed the necessary preprocessing, and evaluated its performance on the test set. | Testing | ILO 2.3 | 2 | 2 | 0 | IMDB model training and evaluation | The model performed decently, but there is room for improvement, especially in terms of validation accuracy. I might consider experimenting with different architectures or adding dropout to prevent overfitting.
| Done | Training the Reuters News Dataset Model | I followed the steps for training and evaluating the neural network using the Reuters dataset, performed data preprocessing, and evaluated the model’s performance using accuracy metrics. | Testing | ILO 2.3 | 2 | 2 | 0 | Reuters dataset model training | The model achieved reasonable results, but there might be room for improvement by fine-tuning hyperparameters or using techniques like regularization
| Done | California Housing Dataset Model | I trained the neural network on the California housing dataset and evaluated its performance using the mean squared error (MSE) loss function | Testing | ILO 2.3 | 1 | 1 | 0 | California housing dataset model training | The model was effective, but it may benefit from further tuning with different optimizers or architectures to improve prediction accuracy and reduce overfitting.
| Done | Quiz | I completed the quiz related to Chapter 3 of Deep Learning with Python | Study | ILO 3.2 | 3 | 3.5 | 0.5 | Link to the completed quiz | The quiz was too effective for me
| Done | Chapter 3 | I studied Chapter 3 of "Deep Learning with Python," covering how to improve model performance, interpret learning curves, and adjust parameters like batch size and activation functions. | Research | ILO 2.3 | 3 | 4 | 1 | Chapter 3 | Chapter 3 helped me understand the importance of adjusting the learning curve and identifying overfitting by analyzing loss and accuracy curves
| Done | Video Review | I watched the video titled "How to Evaluate Machine Learning Models" on YouTube. The video covered the common evaluation metrics | Study | ILO 4.1 | 1 | 1 | 0 | https://youtu.be/LbX4X71-TFI | The video was a great refresher on evaluation metrics, especially for classification tasks. It clarified how precision and recall are important for imbalanced datasets
25/2/25 | Done | Keras Metrics: | I explored the Keras Metrics documentation to understand various metrics used in model evaluation | Research | ILO 4.1 | 1 | 1 | 0 | https://keras.io/api/metrics/ | After reviewing Keras metrics, I gained a clearer understanding of the flexibility Keras provides for model evaluation.
| Done | Scikit-Learn Metrics | I explored scikit-learn's evaluation metrics to understand how it can be used in model evaluation. | Research | ILO 3.2 | 1 | 1 | 0 | https://scikit-learn.org/stable/modules/model_evaluation.html | The scikit-learn metrics offer a more detailed approach to evaluating the performance of models, especially through tools like the confusion matrix and classification report
| Done | Model Evaluation Metrics | I also implemented two different methods for splitting datasets (train/validation/test) in Keras using scikit-learn’s train_test_split. | Testing | ILO 6.2 | 2 | 2 | 0 | Jupyter notebook | I gained a better understanding of which metrics are most useful for different types of models. It was important to understand when to use metrics like precision and recall versus accuracy, especially for imbalanced datasets
| Done | Practical Assignment II | I followed the steps for building and evaluating a Multilayer Perceptron (MLP) model on the MNIST dataset | Testing | ILO 2.3 | 3 | 3.5 | 0.5 | Practical Assignment II | By using the MNIST dataset, I was able to visualize and analyze the model's performance, particularly through the loss and accuracy curves. I noticed that early stopping helped prevent overfitting
| Done | MLP Model Training and Evaluation | Preprocessed data and built MLP model with different learning rates for comparison. | Study | ILO 2.3 | 2 | 3.5 | 1.5 | MLP Model Performance | I learned how different learning rates affect the model's performance and stability during training.
| Done | Figma Design | I followed the Figma beginner tutorial to create a basic social media app design, learning wireframing, high-fidelity design, prototyping | Design | ILO 4.1 | 1 | 1 | 0 | https://help.figma.com/hc/en-us/sections/4405269443991-Figma-for-Beginners-tutorial-4-parts- | he tutorial helped me understand essential design tools and techniques in Figma
| Done | Completed the "UX Foundations: Interaction Design" course on LinkedIn Learning, learning key concepts like affordance | Completed the "UX Foundations: Interaction Design" course on LinkedIn Learning, learning key concepts like affordance | Study | ILO 2.3 | 3 | 3.5 | 0.5 | Course Evidence | The course provided a deep understanding of how interactions shape user experiences
| Done | User Interface Design | Finished the "Interaction Design: Interface" course, where I explored UI design | Study | ILO 2.3 | 4 | 4.5 | 0.5 | Course Evidence | The course enhanced my knowledge of creating high-fidelity interfaces and how different interaction types and their timings can influence usability and engagement.
13/3/2025 | Done | Quiz | Completed interaction design tasks and quizzes | Study | ILO 2.3 | 1 | 1.5 | 0.5 | Quiz Evidence | I gained a deeper understanding of how user interaction is designed
| Done | Design From Figms | Created a sleek mobile app design for tracking plant health from figma | Design | ILO 2.3 | 4 | 5 | 1 | Figma Evidence | I explored various design approaches to create a user-friendly app.
| Done | Neural Network Architecture Study | I studied perceptrons, sigmoid neurons, and multilayer architectures to understand neural network structures. | Study | ILO 2.3 | 1 | 1 | 0 | https://youtu.be/aircAruvnKk | Understanding the components like weights, biases, and activation functions helped me grasp how data flows through the network.
2025-12-03 | Done | Visualizing Neural Networks | I watched Grant Sanderson’s video to visualize how neural networks compute and process image data. | Study | ILO 3.2 | 1 | 0.5 | -0.5 | https://youtu.be/IHZwWFHWa-w | The animation made abstract neural concepts like layers and training more intuitive and easier to understand.
| Done | DataLab Preparation Quiz Completion | I completed the DataLab Preparation quiz by answering questions about perceptrons, MLPs, and gradient descent. | Study | ILO 2.3 | 4 | 4 | 0 | Week 3 Quiz Screenshot | The quiz helped reinforce my understanding and identify which concepts I needed to review more carefully before the implementation lab.
| Done | Gradient Descent Notebook Screenshot Workload Heading: | I implemented a naive gradient descent algorithm in the Week 3 student notebook using a single trainable parameter. | Study | ILO 2.3 | 2 | 4 | 2 | Jupyter notebook | Visualizing each update step helped me understand how gradient descent iteratively minimizes loss in a neural network.
| Done | MLP From Scratch Notebook | I implemented a full multilayer perceptron from scratch using Python without deep learning libraries. | Study | ILO 2.3 | 4 | 4 | 0 | Notebook: MLP Implementation | Building each function manually helped me understand how neural networks work under the hood, especially forward pass and gradient descent. Evidence Heading:
|  |  |  | Total Hours |  | 46 | 53.5 | 7.5
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 4 Evidence | This section is for all evidence linked in Week 4, and you can find it divided by days below | Evidencing |  | 0 | 0 | 0 |  | https://github.com/BredaUniversityADSAI/2024-25c-fai1-adsai-CerenKurt243910/tree/main/Week%204
| Done | Keras CNN Training & Quiz | I completed the full DataCamp course on Image Modeling with Keras and answered detailed questions about CNN layers and architecture. | Study | ILO 2.3 | 4 | 4 | 0 | DataCamp Completion | This course helped me connect theoretical CNN concepts with real-world Keras implementations, especially how convolution and pooling work.
| Done | CNN Concepts from Python Book | I studied chapters on convolutional networks and Keras workflows from the Deep Learning with Python book to prepare for the DataLab. | Research | ILO 2.3 | 3 | 3.5 | 0.5 | Chapter 7 & 8 | The sections provided solid insight into how CNNs are structured, trained, and evaluated, especially for small datasets like mine.
2025-10-03 | Done | Quiz | quiz on Brightspace, answering detailed questions about convolution operations and CNNs in Keras. | Study | ILO 2.3 | 3 | 4 | 1 | CNN Quiz Screenshot | The quiz helped me reinforce what I learned from the course and reading materials, especially the role of layers and filters in CNNs.
| Done | CNN Training Process | I trained my CNN model using training data and monitored accuracy and loss over multiple epochs. | Study | ILO 3.2 | 2 | 2 | 0 | Deep Learning Template | Seeing the training process in action helped me understand the balance between underfitting and overfitting.
| Done | Usability Testing Course Completion | I completed the LinkedIn Learning course on usability testing and uploaded the certificate to GitHub. | Study | ILO 3.2 | 2 | 2.5 | 0.5 | Course Evidence | The course helped me understand how to plan user tests effectively and identify key usability issues in a structured way.
2025-03-11 | Done | UX Research Theory Study | I studied chapters from the UX Research Field Guide to learn about planning, methods, and analysis in user research. | Research | ILO 4.1 | 2 | 2 | 0 | https://youtu.be/n8MnoJyl3W4 | Learning the difference between qualitative and quantitative research gave me a better foundation to design meaningful user tests.
| Done | User Testing Quiz | I completed the Brightspace quiz answering questions about user research, usability testing, and crowd-sourcing feedback. | Study | ILO 3.2 | 3 | 3.5 | 0.5 | User Testing Quiz Submission | The quiz helped me reflect on how to apply user research methods in my creative brief project more effectively.
2025-12-03 | Done | CNN Iteration with Augmented Data | I applied data augmentation using Keras to expand my dataset and retrained my CNN to evaluate its impact. | Study | ILO 6.2 | 1 | 1 | 0 | Tempalte Evidence | Augmentation made my model more resilient to overfitting and improved validation results slightly.
| Done | CNN Iteration with Pretrained Model | I implemented transfer learning using MobileNet as the base model and trained a custom dense classifier on top. | Study | ILO 3.2 | 1 | 1 | 0 | Template Evidence | Transfer learning boosted performance significantly and reduced training time, showing its power for small datasets.
13/3/2025 | Done | CNN Iteration with Augmented Data | I applied data augmentation using Keras to expand my dataset and retrained my CNN to evaluate its impact. | Study | ILO 6.2 | 1 | 3 | 2 | https://keras.io/api/applications/mobilenet/ | Augmentation made my model more resilient to overfitting and improved validation results slightly.
14/2/2025 | Done | Research on Transfer Learning Models | I reviewed TensorFlow’s Keras Applications documentation to understand available pretrained models and their use cases. | Research | ILO 8.2 | 2 | 3 | 1 | https://www.tensorflow.org/api_docs/python/tf/keras/applications | Exploring different model options helped me choose MobileNet for transfer learning based on performance and resource efficiency.
|  |  |  | Total Hours |  | 24 | 29.5 | 5.5
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 5 Evidence | This section is for all evidence linked in Week 5, and you can find it divided by days below | Evidencing | - | 0 | 0 | 0 |  | https://github.com/BredaUniversityADSAI/2024-25c-fai1-adsai-CerenKurt243910/tree/main/Week%205
| Done | ML Lifecycle Theory | I studied the machine learning project lifecycle and its iterative nature using Chapter 6 from Deep Learning with Python. | Study | ILO 3.2 | 4 | 4 | 0 | Chapter 6 | Understanding each phase helped me better structure my current project and connect it to real-world workflows.
| Done | ML Production – Initial Videos | I watched the first videos from Andrew Ng’s ML in Production course, focusing on project lifecycle and data consistency issues. | Study | ILO 3.2 | 2 | 2 | 0 | https://www.youtube.com/playlist?list=PLkDaE6sCZn6GMoA0wbpJLi3t34Gd8l0aK | The “proof of concept to production” gap was a key insight into why many ML systems fail outside lab settings.
17/3/25 | Done | Quiz – ML Project Lifecycle | I completed the quiz on Brightspace covering ML lifecycle, data strategies, and key deployment concerns. | Study | ILO 3.2 | 4 | 3 | 1 | Week 5 Quiz Screenshot | The quiz made me realize how critical consistent labeling and iterative analysis are in real-life ML projects.
| Done | Modeling & Deployment – ML Course | I watched lessons on deployment challenges, baseline creation, and data-centric modeling from Andrew Ng’s course. | Research | ILO 3.2 | 2 | 1 | 1 | https://www.youtube.com/watch?v=YJsRD_hU4tc&list=PLkDaE6sCZn6GMoA0wbpJLi3t34Gd8l0aK | Learning how to establish human-level performance as a baseline gave me a concrete tool to assess model limits.
| Done | Image Classification Model Improvement | I worked on improving the image classification model by experimenting with data augmentation, transfer learning, and hyperparameter optimization. | Study | ILO 4.1 | 3 | 4 | 1 | Deep Learning Template | Experimenting with multiple techniques helped refine the model and gave insights into optimizing it for better performance.
| Done | Baseline Calculation for HLP | I calculated the Human-Level Performance (HLP) and documented the baselines in my Jupyter notebook. | Study | ILO 4.1 | 3 | 2 | -1 | Deep Learning Template | alculating HLP made me realize how far my model still has to go in achieving competitive performance.
18/3/25 | Done | HCAI Design Reflection | I studied the concepts of Human-Centered AI (HCAI) and compared them to my project’s design using the insights from the provided article. | Study | ILO 2.3 | 1 | 1 | 0 | http://ww1.examplelink.com/?terms=create%20a%20domain%20for%20website,register%20a%20url%20address,get%20a%20free%20domain%20for%20website | The article provided a valuable perspective on how AI should be designed with user-centric values, and I plan to integrate this into my design.
| Done | AI Algorithm Design Process | I explored how to design for AI algorithms, focusing on integration, monitoring, and maintaining algorithms post-deployment. | Study | ILO 3.2 | 1 | 3 | 2 | https://design.google/library/simulating-intelligence | Learning how to implement and monitor AI algorithms is crucial for ensuring long-term efficiency and fairness in real-world applications.
| Done | Machine Learning Lifecycle Definition | I defined each phase of the Machine Learning Project Lifecycle, focusing on a skin lesion classification model, and documented it for my creative brief project. | Study | ILO 3.2 | 2 | 2 |  | https://towardsdatascience.com/augmenting-images-for-deep-learning-3f1ea92a891https://towardsdatascience.com/augmenting-images-for-deep-learning-3f1ea92a891c | Mapping out the entire ML lifecycle helped me understand how each phase is interdependent, and the importance of iteration.
19/3/25 | Done | Quiz on ML Lifecycle | completed the quiz on the Machine Learning Project Lifecycle, focusing on defining project goals, ethical considerations, and model evaluation metrics. | Study | ILO 2.3 | 3.5 | 2 |  | Quiz ScreenShot | The quiz reinforced my understanding of how to define and evaluate a machine learning model's performance across different stages.
20/3/25 | Done | Human-Centered AI Video | I watched the video on Human-Centered AI design to better understand how user needs and ethical considerations should shape AI systems. | Research | ILO 3.2 | 2 | 3 |  | https://www.youtube.com/watch?v=4W2kXBBFDw4&pp=ygUYaHVtYW4gY2VudGVyZWQgYWkgZGVzaWdu0gcJCX4JAYcqIYzv | The video gave me practical insights into balancing technology with human values, which will help refine my design process.
21/3/25 | Done | ML in Production Video Insights | I watched the video series on Machine Learning in Production to understand the lifecycle and deployment challenges of ML models. | Research | ILO 2.3 | 3 | 2 |  | https://www.youtube.com/watch?v=Mrv3CZNWYEg&pp=ygUObWwgcHJvZHVjdGlvbiDSBwkJfgkBhyohjO8%3D | These videos helped clarify the practical steps involved in deploying and maintaining machine learning systems in real-world settings.
| Done | Error Analysis Video Insights | I watched the videos on error analysis and performance auditing from the course and learned how to identify errors in machine learning models. | Study | ILO 2.3 | 1 | 0.5 |  | https://youtu.be/kPtotLrFCVw | Error analysis will help me find areas of improvement for my model, focusing on the most common mistakes.
| Done | Skewed Dataset and Metric Selection | I watched the videos explaining skewed datasets and how to select appropriate metrics like F1 score for performance evaluation. | Study | ILO 2.3 | 1 | 0.5 |  | https://www.youtube.com/playlist?list=PLkDaE6sCZn6GMoA0wbpJLi3t34Gd8l0aK | F1 score is essential for evaluating models with imbalanced datasets, which is useful for my project’s dataset.
| Done | Quiz on Error Analysis | I completed the quiz covering error analysis, performance auditing, and data iteration techniques. | Study | ILO 3.2 | 2 | 2.5 |  | Quiz Evidence | The quiz helped me solidify my understanding of these concepts and how to apply them to my project.
| Done | Error Analysis Insights | I performed error analysis on my image classification model, identifying and categorizing misclassified images. | Study | ILO 6.2 | 4 | 4 |  | Deep Learning Template | The error analysis helped me identify which types of errors are affecting model performance, guiding improvements.
| Done | Error Categories Analysis | I identified and categorized errors in my misclassified images, focusing on categories like "background confusion" and "occlusions." | Study | ILO 2.3 | 2 | 2.5 |  | Deep Learning Template | Categorizing errors made it clear which aspects of my dataset and model need improvemen
|  |  |  | Total Hours |  | 40.5 | 39 | -1.5
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 6 Evidence | This section is for all evidence linked in Week 6, and you can find it divided by days below | Evidencing | - | 0 | 0 | 0 |  | https://github.com/BredaUniversityADSAI/2024-25c-fai1-adsai-CerenKurt243910/tree/main/Week%206
24/3/25 | Done | Data Definition | I explored the challenges of data definition in machine learning, particularly with ambiguous labeling. | Research | ILO 2.3 | 2 | 2 | 0 | https://youtube.com/playlist?list=PLkDaE6sCZn6GMoA0wbpJLi3t34Gd8l0aK | realized that properly defining data is crucial to avoid ambiguity, especially when labels are unclear, and this affects the accuracy of machine learning models.
| Done | Watched Videos on Labeling Ambiguity | Watched videos on how ambiguous data labeling can cause errors in model training. | Research | ILO 4.1 | 4 | 4 | 0 | https://www.youtube.com/watch?v=hbqxEJisBHo&list=PLkDaE6sCZn6GMoA0wbpJLi3t34Gd8l0aK | This part made me realize how important it is to clarify labeling guidelines and how ambiguity can lead to significant confusion during training, especially when dealing with more complex datasets.
25/3/25 | Done | Completed DataLab Quiz for Week 6 | Completed the quiz titled "DataLab Preparation (Week 6, DataLab I, Monday)" on Brightspace, covering the key concepts from the Machine Learning Project Lifecycle. | Study | ILO 6.2 | 3 | 3.5 | 0.5 | Quiz Evidence | The quiz helped solidify my understanding of data pipeline concepts and the challenges of labeling and organizing data in machine learning projects. It made me more aware of how these phases affect the success of a model.
| Done | Problem Definition and Diagram Completion | I created the DAPS diagram and completed the task of defining the problem, aligning it with business value and consumer needs | Study | ILO 2.3 | 2 | 4 | 2 | DAPS Diagram | This task helped me clarify the purpose of the application and how it fits within the business goals and market needs, ensuring the project is well-structured and aligned.
| Done | Business Understanding Template | I completed the business understanding template, detailing the main idea, market research, consumer needs, and how the app will address stakeholder needs. | Study | ILO 8.2 | 5 | 4 | -1 | Business Understanding Template | This exercise gave me a clearer understanding of how the application will solve the market's problems and meet the needs of plant owners, ensuring it provides real value.
27/3/25 | Done | Completed DataLab Quiz for Week 6 | Completed the quiz titled DataLab Preparation (Week 6, DataLab II, Thursday) on Brightspace, reflecting on the preparation for the think-aloud study. | Study | ILO 8.2 | 6 | 6 | 0 | Completed DataLab Preparation Quiz | The quiz was helpful in solidifying my understanding of the key aspects of the study and helped me review what needs to be addressed during the think-aloud study.
| Done | Tutuorial | Reviewed the article on free transcription tools from AI Media, analyzing different options and understanding their potential uses for transcribing audio and video content efficiently. | Study | ILO 2.3 | 3 | 4 | 1 | https://www.ai-media.tv/knowledge-hub/insights/free-transcription-tools/ | The review of free transcription tools highlighted several options that can be useful for improving accessibility and creating accurate transcriptions. It helped me better understand the trade-offs between features and limitations of free tools.
| Done | Quiz |  | Study | ILO 2.3 | 2 | 2 | 0 | Business Understanding Template
|  |  |  | Total Hours |  | 27 | 29.5 | 2.5
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 7 Evidence | This section is for all evidence linked in Week 7, and you can find it divided by days below | Evidencing |  |  |  | 0
| Done | Tutuorial | I watched the video on "Introduction to Explainable AI" by Google Cloud to learn the basics of XAI and its importance in making AI systems more transparent and understandable. | Study | ILO 1.3 | 1 | 1 | 0 | https://youtu.be/6xePkn3-LME
| Done | Tutuorial | I watched the video on "An AI Scientist Turned a Breast Cancer Diagnosis Into a Tool to Save Lives" to see a real-world application of AI in healthcare, showcasing how deep learning-based computer vision can help diagnose cancer. | Study | ILO 1.3 | 1 | 1 | 0 | https://youtu.be/qGoCUpa8Qbo
| Done | Tutuorial | I watched the video titled "Do We Really Want Explainable AI?" by Edward Ashford Lee to explore the arguments for and against XAI and gain a deeper understanding of its practical implications. | Study | ILO 1.3 | 1 | 1 | 0 | https://youtu.be/Yv13-UPZNGE
|  |  |  | Total Hours |  | 3 | 3 | 0
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
ALL WEEK | Done | All Week 8 Evidence | This section is for all evidence linked in Week 8, and you can find it divided by days below | Evidencing |  | 0 | 0 | 0
2005-04-08 | Done | T-test | I did t-Test after A/B test responses | Study | ILO 1.3 | 1 | 1 | 0
8/4l25 | Done | A/B test | I did A/B testing for choosing my final design | Study | ILO 2.3 | 2 | 2 | 0
2025-04-10 | Done | Demo video | I did a Demo Video for Finalizing Human-Centered Template | Study | ILO 1.3 | 2 | 2 | 0
2025-04-11 | Done | Presentation | I did Presentation about my project | Study | ILO 2.3 | 1 | 1 | 0
|  |  |  | Total Hours |  | 6 | 6 | 0
|  |  |  | Total hours this block |  | 198.5 | 216.5 | 18

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.3 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 3 | 10
ILO 2.3 | 8 | 13 | 43.5 | 11.5 | 8.5 | 12 | 0 | 3 | 99.5
ILO 3.2 | 3.5 | 5.5 | 5 | 9 | 20.5 | 0 | 0 | 0 | 43.5
ILO 4.1 | 0 | 5 | 3 | 2 | 6 | 4 | 0 | 0 | 20
ILO 6.2 | 0 | 0 | 2 | 4 | 4 | 3.5 | 0 | 0 | 13.5
ILO 8.2 | 0 | 0 | 0 | 3 | 0 | 10 | 0 | 0 | 13
ILO 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HOURS PER WEEK | 11.5 | 27.5 | 53.5 | 29.5 | 39 | 29.5 | 3 | 6
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.3
Unplanned | Meeting | ILO 2.3
Blocked | Programming | ILO 3.2
In-Progress | Research | ILO 4.1
Done | Testing | ILO 6.2
Delayed | Workshop | ILO 8.2
Cancelled | Planning | ILO 9.1
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break