## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Task reflection / notes
Week 1
week plan: | time series basics, practiced data visualisation
Known Risks | no risk and no issues
2025-05-06 | Done | block D introduction | I was unable to attend the kick off activities due to personal reasons | Unplanned | ILO 6.3 | 1 | 1 | 0 | Missing the session made it harder to start, but reviewing the material helped me catch up
| Done | sql practice setup | I installed Postgresql and completed practice sql queries using the block D dataset | Study | ILO 6.3 | 5 | 5 | 0 | The exercises made me feel more confident about working with large financial datasets
| Done | datacamp sql | I completed chapter 1 of the Introduction to sql course on Datacamp | Study | ILO 6.3 | 5 | 5 | 0 | The course was a good refresher and clarified differences between relational and SQL databases.
| Done | client dataset review | I explored the move tickers client description and reviewed the provided datasets | Research | ILO 6.3 | 0.5 | 0.5 | 0 | Learning about the client’s goals helped me see how data can support real-world finance
2025-05-07 | Done | data warehouses | I studied the basics of data warehouses OLAP vs OLTP and dimensional modeling using the kimball method | Study | ILO 6.3 | 3 | 3 | 0
| Done | schema design | I explored schema design, normalization vs denormalization | Study | ILO 6.3 | 0.5 | 0.5 | 0 | It helped me realize how database design
| Done | advanced sql practice | I practiced using case statements and subqueries on the block D dataset | Programming | ILO 6.3 | 5 | 5 | 0 | Writing more advanced queries boosted my confidence
2025-05-08 | Done | sql upskilling | I practiced intermediate sql including date/time functions and window functions on financial data | Programming | ILO 6.3 | 5 | 5 | 0
| Done | sql query | I solved complex sql queries such as rolling averages, lag functions | Programming | ILO 6.3 | 5 | 5 | 0 | Some queries were difficult at first, but trying different approaches really improved my logic.
| Done | database design | I studied key database design considerations like security, privacy | Research | ILO 6.3 | 1 | 1.5 | 0.5
2025-05-09 | Done | sql exercise | I completed multi level sql exercises, including filtering, math functions | Programming | ILO 6.3 | 3 | 4 | 1
| Done | meeting with my team | I collaborated with my team to explore the dataset and discussed useful features for the ml model | Meeting | ILO 6.3 | 1 | 1 | 0 | Working together gave me a better understanding of which data points matter for predictions and they were good
| Done | Schema Review | I reviewed our schema options | Planning | ILO 6.3 | 6 | 4 | -2
|  |  |  | Total Hours |  | 41 | 40.5 | -0.5
Week 2
week plan: | financial time series data applied ARIMA modelling and explored forecasting methods
Known Risks | towards the end of the week I wasn't feeling very well
2025-05-12 | Done | time series basics | I completed Datacamp course on manipulating time series data in python | Study | ILO 1.4 | 2 | 2 | 0
| Done | AI business model canvas | Studied the AI business canvas and reviewed project value data and stakeholder planning | Study | ILO 3.3 | 4 | 4 | 0 | It helped me understand how AI projects align with business goals
| Done | legal and ethical AI | Studied legal and ethical AI frameworks and assessed risk level of my AI system | Research | ILO 2.4 | 1.5 | 2 | 0.5 | It helped me structure the project clearly and match AI features to business goals
2025-05-13 | Done | business model canvas | Refined my AI project idea clarified the value proposition, and completed the business model canvas | Study | ILO 1.4 | 3 | 3 | 0
| Done | legal risk GDPR | Completed task 2.1 by evaluating GDPR and AI act risks for my proposed AI system | Study | ILO 3.3 | 3 | 3 | 0 | I learned how to check if an AI project is high-risk and what legal steps it requires
| Delayed |  |  |  | ILO 2.4
| Done | block C retake | I just studied infograph part and templates for block C | Study | ILO 3.3 | 3 | 4 | 1
| Done | guest lecture | I just attended a guest lecture on time series by juha peltomaki | Lecture | ILO 8.4 | 4 | 4 | 0 | I gained new insights into real-world time series applications
2025-05-14 | Done | time series graphs | I used python to make different graphs for time series data like line plots and boxplots | Study | ILO 2.4 | 2 | 2 | 0 | I learned how to show patterns trends and changes in time series using simple code
| Done | smarter goal | I wrote my smarter professional development goal for this block | Study | ILO 6.3 | 5 | 5 | 0
2025-05-15 | Done | ARIMA model practice | I just explored ARIMA models using python and practiced forecasting | Study | ILO 6.3 | 1.5 | 3 | 1.5 | It was challenging at first but coding helped me understand the models more clearly
| Done | datacamp course | I finished the time series analysis in python course on datacamp and got my certificate | Study | ILO 9.2 | 2 | 4 | 2
2025-05-16 | Unplanned | time series cleaning | I worked with real stock data by resampling it and fixing missing values | Research | ILO 3.3 | 2 | 1.5 | -0.5 | I missed the datalab session because I was really sick but I filled absence form and I did all tasks but I missed the review session with my mentor
| Done | time series plots | I made simple plots to show trends, rolling averages and stock volatility | Study | ILO 4.2 | 4 | 4 | 0
| Done | time series forecasting | I used basic forecasting methods like naive and ARIMA | Study | ILO 9.2 | 5 | 5 | 0 | Trying different methods helped me
|  |  |  | Total Hours |  | 42 | 46.5 | 4.5
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks
2025-05-19 | Done | individual project proposal | I worked on my individual project proposal and defined the problem, data, and target users. | Study | ILO 2.4 | 2 | 2 | 0 | Writing the proposal helped me focus my idea and connect it with real-life use cases.
| Done | watch lectures | Watched videos about AI risk and GDPR basics | Study | ILO 2.4 | 1 | 2 | 1
| Done | take notes | Took notes during lectures to remember important points | Lecture | ILO 2.4 | 4 | 4 | 0
20/5/25 | Done | ARIMA and regression | I read online sources about ARIMA and linear regression for time series. | Study | ILO 2.4 | 4 | 4 | 0 | I made me realize that simple models can be powerful with the right preprocessing.
| Done | idea feedback | I discussed my project idea with a teammate to get feedback. | Study | ILO 2.4 | 4 | 4 | 0 | Their comments helped me improve my target audience and evaluation strategy.
| Done | value proposal | I wrote a short paragraph explaining why my project idea is useful in real life. | Study | ILO 2.4 | 5 | 5 | 0
21/5/25 | Done | ML planning | I planned how I will build the model step by step for my proposal. | Study | ILO 2.4 | 3 | 3 | 0 | Structuring the model workflow made it easier to write the rest of the proposal.
| Done | reviewing deadline checklist | I reviewed the checklist to make sure I included everything required in the proposal. | Study | ILO 4.2 | 2 | 1 | -1
| Done | practice risk classification | Practiced classifying AI systems using AI Act examples | Study | ILO 2.4 | 5 | 5 | 0 | Learned to decide if a system is high risk or not
22/5/25 | Done | join team meetings | Attended kickoff meeting to discuss project risks | Study | ILO 3.3 | 0.5 | 0.5 | 0 | Shared my thoughts with the team
| Done | practice applying rules | Tried to apply GDPR rules to our project example | Research | ILO 2.4 | 1 | 2 | 1
| Done | read ai act texts | Read parts of the EU AI Act related to risk classification | Study | ILO 2.4 | 4 | 4 | 0 | Some parts were hard but important
| Done | Time Series | Learned and worked about SHAP and LIME explainability methods | Programming | ILO 2.4 | 4 | 7 | 3
2025-05-23 | Done | reflect on week | Wrote reflections on what I did well and what was hard | Planning | ILO 3.3 | 1 | 1 | 0
|  |  |  | Total Hours |  | 40.5 | 44.5 | 4
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | no risk and no issues
26/5/25 | Done | review individual proposals | Read all team members' AI Canvas proposals | Meeting | ILO 6.3 | 4 | 4 | 0
| Done | contribute to data description | Wrote about datasets and how they support project goals | Planning | ILO 6.3 | 2 | 2 | 0 | Helped clarify data sources and their relevance
| Done | team meeting on proposal | Discussed and agreed on unified project problem and objectives | Planning | ILO 6.3 | 4 | 4 | 0 | Made sure everyone agreed on clear goals
27/5/25 | Done | write legal risk part | Explained how our AI system follows GDPR and AI Act | Study | ILO 3.3 | 5 | 5 | 0
| Done | retrospective preparation | Prepared notes for group retrospective meeting | Meeting | ILO 3.3 | 4 | 4 | 0 | Reflected on teamwork and project progress
| Done | attend retrospective | Participated in group retrospective session | Meeting | ILO 3.3 | 4 | 4 | 0 | Gave feedback and learned from teammates
28/5/25 | Done | organize Trello board | Updated task statuses and deadlines on Trello board | Planning | ILO 3.3 | 5 | 5 | 0 | Helped keep team organized and aware of deadlines
| Done | submit final reports | Uploaded final team proposal and legal risk assessment | Study | ILO 6.3 | 4 | 4 | 0
29/5/25 | Done | review GDPR guidance | Read more on GDPR to better understand compliance requirements | Study | ILO 3.3 | 6 | 6 | 0
| Done | plan next week coding tasks | Set goals for building the machine learning model | Planning | ILO 4.2 | 4 | 4 | 0 | Organized priorities for efficient work
30/5/25 | Done | exploratory data analysis (EDA) | Explored datasets using SQL queries to understand data patterns | Research | ILO 2.4 | 3 | 3 | 0
|  |  |  | Total Hours |  | 45 | 45 | 0
Week 5
week plan: | 1) workignon model 2)creating the notebook 3)connecting to database
Known Risks | Being so sleepy and i had also some error about my pythin version.
2025-02-06 | Done | Standup | We had a stand-up meeting with our group members to review our plans and tasks for the upcoming week. | Meeting | ILO 2.4 | 2 | 2 | 0 | There have been some changes in Trello.
| Done | working on the model | I tried several models, including regression, MLO, XGBoost, and a few others. | Programming | ILO 8.4 | 6 | 6 | 0 | The results are good, but I need to discuss them with my group members tomorrow.
2025-03-06 | Done | Standup | The results are good, but I need to discuss them with my group members tomorrow. | Meeting | ILO 2.4 | 1 | 1 | 0
| Done | Trying diffrent model | I went through the model again and trained other models to compare their results. | Programming | ILO 8.4 | 4 | 4 | 0 | The clustering also performed well!
| Done | Sql week 1 | I worked on the SQL tasks from Week 1 again to finalize them and document the evidence in Learning Log Section C | Programming | ILO 1.4 | 6 | 6 | 0 | I documented the evidence in the learning log, and I will review it again at the end of the block.
2025-04-06 | Done | Standup | We had a stand-up meeting to review what remains to be done and what we did wrong. | Meeting | ILO 1.4 | 1 | 1 | 0 | We discussed the work we’re currently doing. We've finished almost everything—just a few tasks still need to be discussed.
| Done | Workingon the model | I worked on the model, tried some models again, and evaluated their performance. | Programming | ILO 8.4 | 8 | 8 | 0
2025-05-06 | Done | Standup | We had the last stand-up of the week and discussed what still needs to be done and what can be left out. | Meeting | ILO 1.4 | 1 | 1 | 0
| Done | Model improvement | I'm still working on the model deployment, and it still needs some improvements. | Programming | ILO 8.4 | 6 | 6 | 0 | I will talk to Filip about this model.
2026-06-06 | Done | Testing model | Today, I also spent some time testing the models and checking the accuracy of each one. | Testing | ILO 8.4 | 5 | 5 | 0 | It needs to be discussed.
|  |  |  | Total Hours |  | 40 | 40 | 0
Week 6
week plan: | 1) Finish with the modeling
Known Risks | Train Strikes
2025-09-06 | Done | Working on the model | i work on the model and and try to evalute and again see what can i do with it. | Study | ILO 8.4 | 6 | 6 | 0 | It still needs work.
| Done | Stand up | We had a stand-up meeting to discuss the direction of the project. | Meeting | ILO 1.4 | 1 | 1 | 0
2025-10-06 | Done | Workig on the model | i work on the model and and try to evalute and again see what can i do with it. | Programming | ILO 8.4 | 2 | 2 | 0 | the regression part still need some work.
| Done | Stand up | We had a stand-up meeting to discuss the direction of the project. | Meeting | ILO 4.2 | 5 | 5 | 0
2025-11-06 | Done | MLOps | i worked on the model versions and model and performance development. | Programming | ILO 1.4 | 7 | 7 | 0 | the model versions has some difficulties.
| Done | MLOps | i worked on the model versions and model and performance development. | Programming | ILO 1.4 | 4 | 4 | 0 | the model versions has some difficulties.
2025-12-06 | Done | Filing the Templates | i fill in the templates. | Research | ILO 3.3 | 6 | 6 | 0
| Done | Stand up | We had a stand-up meeting to discuss the direction of the project. | Meeting | ILO 1.4 | 5 | 5 | 0
| Done | working on the model | I worked on the model, tried some models again, and evaluated their performance. | Programming | ILO 6.3 | 6 | 6 | 0 | The clustering also performed well!
13/6/25 | Done | Workig on the model | i work on the model and and try to evalute and again see what can i do with it. | Meeting | ILO 8.4 | 4 | 4 | 0 | still need some work.
|  |  |  | Total Hours |  | 46 | 46 | 0
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
15/6/25 | Done | finalize agenda minutes | Completed and organized all agenda minutes, placed in correct folders | Study | ILO 3.3 | 2 | 2.5 | 0.5
| Done | review final deliverables | Reviewed all project files and presentation materials with the team | Testing | ILO 3.3 | 4 | 3 | -1 | Team collaboration ensured completeness
16/6/25 | Done | update Trello board | Updated and checked Trello board for task status and progress | Study | ILO 3.3 | 1 | 1.5 | 0.5
| Done | prepare presentation slides | Prepared my sections focusing on results, linear regression, classification | Design | ILO 6.3 | 3 | 3 | 0 | Focused on clear and simple explanations for presentation
| Done | practice presentation | Rehearsed presentation, improved timing and clarity | Study | ILO 6.3 | 5 | 5 | 0
| Done | support team fixes | Helped teammates with small fixes in presentation and reports | Study | ILO 3.3 | 5 | 5 | 0 | Assisted team members to polish final outputs
17/6/25 | Done | retrospective session | Led the group retrospective, gave constructive feedback | Meeting | ILO 3.3 | 1 | 1 | 0 | Reflections helped improve team understanding
| Done | organize final folders | Ensured all files and folders were named and stored properly | Evidencing | ILO 3.3 | 1 | 1.5 | 0.5
| Done | coordinate final submissions | Coordinated submission of project deliverables with team | Study | ILO 3.3 | 2 | 2 | 0
| Done | code documentation | added PEP257 style docstrings to key functions | Study | ILO 3.3 | 3 | 3 | 0 | Improved code readability and maintainability
18/6/25 | Done | group documentation collaboration | reviewed group’s individual contribution documentation file | Study | ILO 3.3 | 1 | 1 | 0 | Checked team member contributions for accuracy
| Done | group documentation | coordinated with team to finalize and agree individual contributions | Study | ILO 1.4 | 5 | 5 | 0
| Done | daily stand-up participation | Attended and contributed actively in daily stand-up meetings | Meeting | ILO 3.3 | 0.5 | 0.5 | 0
19/6/25 | Done | manage team tasks | Assigned and tracked tasks to keep team on schedule | Planning | ILO 3.3 | 1 | 1 | 0
| Done | reflect on group experience | Thought about teamwork, communication, and leadership lessons | Meeting | ILO 3.3 | 5 | 5 | 0 | Realized the importance of clear communication and collaboration
20/6/25 | Done | deliver final presentation | Presented my part confidently to peers and client | Study | ILO 6.3 | 1 | 1 | 0
|  |  |  | Total Hours |  | 40.5 | 41 | 0.5
Total Hours
|  |  |  | Total hours this block |  | 295 | 303.5 | 8.5

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.4 | 0 | 5 | 0 | 0 | 8 | 17 | 5 | 0 | 35
ILO 2.4 | 0 | 4 | 42 | 3 | 3 | 0 | 0 | 0 | 52
ILO 3.3 | 0 | 12.5 | 1.5 | 24 | 0 | 6 | 27 | 0 | 71
ILO 4.2 | 0 | 4 | 1 | 4 | 0 | 5 | 0 | 0 | 14
ILO 6.3 | 31.5 | 8 | 0 | 14 | 0 | 6 | 9 | 0 | 68.5
ILO 8.4 | 0 | 4 | 0 | 0 | 29 | 12 | 0 | 0 | 45
ILO 9.2 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
TOTAL HOURS PER WEEK | 31.5 | 46.5 | 44.5 | 45 | 40 | 46 | 41 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.4
Unplanned | Meeting | ILO 2.4
Blocked | Programming | ILO 3.3
In-Progress | Research | ILO 4.2
Done | Testing | ILO 6.3
Delayed | Workshop | ILO 8.4
Cancelled | Planning | ILO 9.2
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break